## Sheet1
Scope: October 1st 2023 - March 18th 2024 (30 weeks) |  |  |  | Key
[5 empty] | Sprint 1 | Planning
[5 empty] | Sprint 2 | Implementing
[5 empty] | Sprint 3 | Testing and final touches
Task | Week 1 (10/1/23-10/7/23) | Week 2 (10/8/23-10/14-23) | Week 3 (10/15/23- 10/21/23) | Week 4 (10/22/23-10/28/23) | Week 5 (10/29/23-11/4/23) | Week 6 (11/5/23-11/11/23) | Week 7 (11/12/23- 11/18/23) | Week 8 (11/19/23- 11/25/23) | Week 9 (11/26/23- 12/2/23) | Week 10 (12/3/23- 12/9/23) | Week 11 (12/10/23- 12/16/23) | Week 12 (12/17/23- 12/23/23) | Week 13 (12/24/23- 12/29/23) | Week 14 (12/30/23- 1/6/24) | Week 15 (1/7/24- 1/6/24) | Week 16 (1/7/24- 1/13/24) | Week 17 (1/14/24- 1/20/24) | Week 18 (1/21/24- 1/27/24) | Week 19 (1/29/24- 2/3/24) | Week 20 (2/4/24-2/10/24) | Week 21 (2/11/24- 2/17/24) | Week 22 (2/18/24- 2/24/24) | Week 23 (2/24/24- 3/2/24) | Week 24 (3/3/24- 3/9/24) | Week 25 (3/10/24-3/16/24) | Week 26 (3/17/24- 3/23/24) | Week 27 (3/24/24-3/30/24) | Week 28 (3/31/24-4/6/24) | Week 29 (4/7/24-4/13/24) | Week 30 (4/14/24-20/24)
Research the current state of sports prediction methodologies and tools
Research the use of Unity Machine Learning with Python
Specify the sports events we would like to focus on
Investigate potential datasets and APIs related to selected sports events
Collect data for past games, including features like teams, players, scores, and other relevant statistics
Design an initial model architecture for sports predictions
Develop a prototype model using relevant ML libraries
Develop and conduct tests for the model to gauge performance
Develop a schema to store data used for our model efficiently
Design the web app UI/UX and decide on a framework
Develop the necessary front-end components for the website
Integrate the ML model into the site's backend to display predictions
Create meaningful features that can contribute to prediction accuracy
Implement any needed database solutions
Document program architecture
Write comprehensive front-end and developer documentation
Develop and run tests for the web application to ensure we are alerted when functionalities break
Configure recovery solutions for site downtime
Refine the UI/UX based on user feedback
Deploy the web app to a suitable hosting platform/service